| Activity | Duration (Days) | Predecessor | ES | EF | LS | LF | Slack | Critical |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A – Project Initiation | 3 | — | 0 | 3 | 0 | 3 | 0 | Yes |
| B – Requirements Analysis | 4 | A | 3 | 7 | 3 | 7 | 0 | Yes |
| C – System Design | 5 | B | 7 | 12 | 7 | 12 | 0 | Yes |
| D – Development | 6 | C | 12 | 18 | 12 | 18 | 0 | Yes |
| E – Testing & Validation | 4 | D | 18 | 22 | 18 | 22 | 0 | Yes |
| F – Documentation & Final Review | 3 | E |  |  |  |  |  |  |