## Work Breakdown Structure (WBS) – Modified

| WBS ID | Activity Name | Estimated Duration |
| --- | --- | --- |
| 1.0 | Project Initiation & Planning |  |
| 1.1 | Project Overview & Objectives Definition | 1 day |
| 1.2 | Stakeholder Identification | 0.5 day |
| 1.3 | Approval of Project Charter | 1 day |
| 2.0 | Requirements & Scope Definition |  |
| 2.1 | Stakeholder Interviews & Analysis | 2 days |
| 2.2 | Functional Requirements Documentation | 2 days |
| 2.3 | Non-Functional Requirements Definition | 1 day |
| 2.4 | Scope Definition & Validation | 1 day |
| 2.5 | WBS & Schedule Development | 1.5 days |
| 3.0 | System Design |  |
| 3.1 | Information Architecture Design | 2 days |
| 3.2 | UI Wireframes & User Flow Design | 2 days |
| 3.3 | Database Logical Design | 2 days |
| 4.0 | System Development |  |
| 4.1 | User Authentication & Role Management | 3 days |
| 4.2 | Project Workspace & Dashboard Development | 4 days |
| 4.3 | Document Management Module | 3 days |
| 4.4 | Database Implementation & Integration | 2 days |
| 5.0 | Testing & Quality Assurance |  |
| 5.1 | Test Strategy & Test Case Design | 1 day |
| 5.2 | System & Integration Testing | 3 days |
| 5.3 | Issue Resolution & Verification | 2 days |
| 6.0 | Deployment & Closure |  |
| 6.1 | System Deployment & Configuration | 1 day |
| 6.2 | User Guide & Technical Documentation | 2 days |
| 6.3 | Final Review, Report & Presentation | 2 days |